## Sheet1
Priority | Item # | Description | Est | By | Notes | Status
1 |  | Registration System | 2 weeks | Oct 20th
| 1 | Create a database of users
| 2 | Implement a way to hash their user information
| 3 | Store all user information
| 4 | Create a login page
| 5 | Implement a way to match login credentials with the hashed user information in the database
2 |  | Registered student list | 1 week
| 6 | Create a button that will access the student list
| 7 | Create a way to store the student list
|  | Grading table | 1 week
| 8 | Create an editable table
| 9 | Store the table
|  | Automatic grade mails | 1.5 weeks
| 10 | Store instructor’s email based on course
| 11 | Send email to the instructor
|  | Adding users | 2.5 weeks
| 12 | Add teaching assistants to the database of users
|  | Student records | 2 weeks
| 13 | Add teaching assistants to the database of users
| 14 | Store the information
3 |  | Lesson plan display | 1 week
| 15 | Create a button that will access the lesson plan
| 16 | Create a way to store a lesson plan
|  | Lesson plan distributor | 2 weeks
| 17 | Implement a way to create and save a text file
| 18 | Implement a way to share the text file to specific users
|  | Remarker | 1 week
| 19 | Implement a way to verify a password
| 20 | After verification, allow editing
|  | Marking scheme | 2 weeks
| 21 | Implement a way to import documents into the application
| 22 | Implement a way to add the document to a specific tutorial
4 |  | Marker | 1 week
Implement a way to create a lock with a password after one submission of grades
Implement a way to store the password