## Sheet1
Story | To Do | In Process | To verify | Done
As John (professor), I want to be able to register on the system, so that I can have access to the application. |  |  |  | Create a database of users | Richard
|  |  |  | Implement a way to hash their user information | Gregory
|  |  |  | Store all user information | Charlie
|  |  |  | Create a login page | Jay
Bo Fang
As Jim, (teaching assistant), I want to be able to see a list of the students registered in my tutorial, so that I have an easy way to distribute marks. |  | Create a button that will access the student list
Create a way to store the student list
As Jan, (teaching assistant), I want to be able to enter grades for the students enrolled in my tutorial section, so that the grades are recorded for the professor. |  | Create an editable table
Store the table
As Jay, (teaching assistant), I want to have a way to email grade files to the instructor automatically after I input the grades, so that I’ll never forget. |  | Store instructor’s email based on course
Send email to the instructor
As Mary (professor), I want to be able to add teaching assistants to the application according to the courses that they teach, so that they have access to the functionality of the application. |  | Add teaching assistants to the database of users
As May (professor), I want a system that records the students’ information, so that I can access it throughout the semester |  | Create a database for student grades
Store the information
As Bob (teaching assistant), I want to have an application that issues reminders of upcoming tutorials that I have to teach so that I won’t forget my tutorials. | Implement a way to create an android notification
As Bill, (teaching assistant), I want to have a system that displays a lesson plan, so that I can look at the plan on the go. | Create a button that will access the lesson plan
Create a way to store a lesson plan
As Mary (professor), I want to be able to provide lesson plans for the teaching assistants, so that they have tutorial instructions with them at all times. | Implement a way to create and save a text file.
Implement a way to share the text file to specific users
As Mary (professor), I want the teaching assistants to only input marks once, so that they are unable to remark without my consent. | Implement a way to create a lock with a password after one submission of grades.
Implement a way to store the password
As Mary (professor), I want to be able to alter marks, so that errors within the grading are fixed accordingly. | Implement a way to verify a password
After verification, allow editing
Implement a way to match login credentials with the hashed user information in the database
As Jerry (professor), I want to be able to add marking scheme to my tutorial section, so that the teaching assistants know how to mark the assignments. | Implement a way to import documents into the application
Implement a way to add the document to a specific tutorial